## Sheet1
Date | # hours worked | Task
2025-05-23 | 3 | Meeting to plan project
2025-05-27 | 4 | proposal doc
2025-05-28 | 3 | Setup code base, initial app template
2025-06-01 | 3 | Meeting to finalize project idea
2025-06-02 | 2 | Meeting for further project discussion + planning
2025-06-03 | 3.5 | TA Meeting + meeting with project group
2025-06-10 | 2 | TA Meeting + Meeting to split up tasks and duties for the project
2025-06-14 | 1 | Meeting for project report and ironing out the features + D2
2025-06-15 | 6 | pair to set up Firestore, google cloud, api key restrictions, etc
2025-06-21 | 6 | Pair programming for postings page
2025-06-22 | 2 | test and demo prep
2025-06-24 | 0.5 | TA Meeting
2025-06-24 | 3 | Comments feature: database, ui, backend, etc.
2025-07-25 | 3 | prototype doc
2025-07-01 | 5 | clean up code, resolve merge conflicts, test
2025-07-06 | 6 | fix ui, clean up code, associate posts and comments with users, test
2025-07-15 | 0.5 | TA Meeting
2025-07-15 | 3 | My posts feature
2025-07-18 | 3 | consolidate firestore logic and functions in code
2025-07-19 | 5 | Matching feature
2025-07-22 | 0.5 | TA Meeting
2025-07-23 | 5 | Notifications page. Refine match logic
2025-07-24 | 4 | Fix ui, resolve merge conflicts, clean up code, test
2025-07-25 | 5 | arch and design doc
2025-07-26 | 2 | Worked on demo presentation slides, demo prep
2025-07-27 | 5 | Test, meet with group
2025-07-28 | 1 | Pair to finalize and merge code
2025-08-01 | 2 | final report
89