## Sheet1
Date | # hours worked
2025-05-23 | 3 | Meeting with group 1 to plan project (Tutorly App)
2025-05-27 | 3 | project proposal document (D1) + slides, stakeholders, sequence diagram, population of users
2025-05-28 | 3 | Setup code base, initial app template
2025-06-01 | 3 | Meeting to finalize project idea
2025-06-02 | 3 | Cleaning up project proposal document + Meeting for further project discussion + planning
2025-06-03 | 3.5 | TA Meeting + meeting with project group
2025-06-10 | 2 | TA Meeting + Meeting to split up tasks and duties for the project
2025-06-14 | 2 | Working on and cleaning up Buddy team's evaluation (D2)
2025-06-15 | 6 | Pair programming with Selina and Mark to set up Firestore, google cloud, api key restrictions, etc
2025-06-21 | 5 | Beginning work on register and login functionality with firebase authentication, bug fixing, fixing variable names
2025-06-22 | 4.5 | Testing and finishing register and login functionality
2025-06-23 | 5 | Debugging and trying to come up with a fix for why register and login functionality weren't working on other computers
2025-06-24 | 0.5 | TA Meeting
2025-06-25 | 1.5 | Proofreading Prototype Document (D3) + demo presentation's problem statement and project goals(D3)
2025-06-30 | 4.5 | Connecting auth with firebase collection "users" and replacing mock data with User collection for profile page
2025-07-06 | 3 | clean up code + deleting code that is no longer referenced, demo prep, and debugging firebase authentication
2025-07-11 | 0.5 | proofreading Architecture Style Examples (D4)
2025-07-12 | 0.5 | proofreading Design Pattern Examples (D5)
2025-07-15 | 0.5 | TA Meeting
2025-07-16 | 2 | Remove post button, toggle for remove post and report based on ownership of post
2025-07-20 | 4 | Background color for profile picture, with username initial
2025-07-21 | 3.5 | Background color for profile picture, with username initial
2025-07-22 | 0.5 | TA Meeting
2025-07-24 | 2 | Debugging background color delayed update + resolving merge conflicts
2025-07-26 | 1 | Worked on demo presentation slides (D6)
2025-07-27 | 4 | Testing tutorly application, meeting with group to go through demo
2025-07-28 | 3.5 | Tutorly demo prep, and attempting to debug button issues (report, delete post button positioning)
2025-07-29 | 3.5 | TA meeting, final demo prep, fixing last minute bugs regarding userid and courses
2025-07-31 | 4 | Design decisions for Architecture and Design Document (D6)
2025-08-01 | 1 | Proofreading and adding my "What was done by each Group Member" for the Final Status Report (D7)
Total | 83